# NOV-DEC PROGRESS REPORT: PROJECTILE RECONNAISSANCE DEVICE (PRD)

| Project Lead | Sannidhi Avenkar |
| --- | --- |
| Reporting Period | November - December 2025 (Phase 2: Development & Implementation) |
| Date | December 11, 2025 |
| Phase Status | Phase 2 In Progress: Parts Acquisition, Design Finalization, Wireless Communication Methodology, Test Code Creation, and Functionality Development |

# 1. Phase 2 Overview and Team Status

Following the successful completion of Phase 1 (Component Selection and Architecture Finalization in October 2025), Phase 2 focuses on transitioning from theoretical design to practical hardware implementation and firmware development. The project is currently in the middle of this phase, with work progressing towards a fully functional prototype.

## Current Phase Duration

October - November 2025: Planning & Design Refinement

December 2025 onwards: Development & Testing

Status Note: Progress is currently paused due to academic exams, resuming after exam period completion.

# 2. Phase 2 Milestones and Achievements

The following milestones have been targeted and partially completed as of December 2025:

## ✅ Completed Milestones

Parts Acquisition - Essential components ordered and partially received

Design Finalised - Detailed mechanical and electrical design drawings completed

Wireless Communication Methodology Finalised - nRF24L01 communication protocol finalized and documented

## 🔄 In Progress Milestones

Test Code Created - Firmware development for individual sensor modules initiated

Functionality Finalised - Integration testing and full system validation in progress

# 3. Team Member Contributions and Tasks

The development workload is distributed among specialized team members:

| Member | Role | Assigned Tasks | Current Progress |
| --- | --- | --- | --- |
| Sannidhi Avenkar | Project Lead / Frontend & API | Base Station Software & UI | Basic layout completed and finalized; API linking to be done |
| Sneha | Research | Component Selection & Optimization | Parts modified for cost effectiveness (BME280+MQ135, MPU9250) |
| Shubham | Frontend & API | Base Station Dashboard | Basic layout completed and finalized; API linking to be done |
| Varad | Designing & Simulation | Mechanical & Electronics Design | Simulation and testing done for viability; verified capsule dynamics |
| Yash | Embedded Coding | Firmware Development | Working on C++ code for ATMEGA328 microprocessor; sensor drivers in progress |

# 4. Sensor Architecture Refinement (Phase 2 Update)

Based on the research led by Sneha, the sensor suite has been optimized for cost-effectiveness, availability, and firmware complexity:

## 4.1 Environmental Monitoring Stack

Previous Design: BME680 (all-in-one: gas + temperature + humidity + pressure)

Revised Design: BME280 + MQ135

• BME280: Temperature, humidity, and atmospheric pressure monitoring

• MQ135: Air-quality and hazardous-gas detection (CO, CO₂, NH₃, NOx, smoke)

• Advantages: Lower BoM cost, better availability

• Trade-off: MQ135 requires analog calibration (~48 hours warm-up)

## 4.2 Orientation and IMU

Previous Design: BNO055 (on-chip 9-DOF sensor fusion)

Revised Design: MPU9250 (9-axis IMU)

• Firmware Implementation: Software-based sensor fusion algorithm

• Advantages: Significantly lower cost, flexible calibration, better availability in India

• Trade-off: Increased firmware complexity

# 5. Budget Status and Financial Update

The project has maintained strict financial discipline with the sensor revisions:

| Budget Category | Amount | Status |
| --- | --- | --- |
| Components Procured (Current) | ₹1,151 | Purchased - Essential components only |
| Remaining Budget | ₹3,849 (Approx) | Reserved for remaining components |
| Total Project Budget | ₹5,000 (Current Phase) | On track - Well under ₹10,000 cap |

## Budget Impact of Sensor Changes

• BME280 + MQ135 combo: ~₹500-700 (vs ₹1200+ for BME680)

• MPU9250: ~₹400-500 (vs ₹900+ for BNO055)

• Net Savings: ~₹1400-1500 redirected to mechanical fabrication

# 6. Technical Progress Summary

## 6.1 Hardware Development

Component Verification: Core components tested

Breadboard Assembly: Initial prototype assembly started

PCB Design: Schematic finalization underway

## 6.2 Wireless Communication System

| Parameter | Specification |
| --- | --- |
| Protocol | SPI-based nRF24L01 (2.4 GHz ISM) |
| Payload Size | 32 bytes (LiDAR + MPU9250 + Environmental) |
| Transmission Freq | 10-50 Hz (configurable) |
| Range | 100-500 meters (open space) |

## 6.3 Firmware Development (Yash - Embedded Team)

Individual sensor libraries created and tested:

LiDAR-Lite v3: Basic range measurement code compiled

MPU9250 IMU: Raw sensor data acquisition initiated

BME280: I2C driver implemented

MQ135: Analog calibration protocol designed

nRF24L01: Wireless transmission test code created

# 7. Updated Bill of Materials (BoM)

| Category | Component | Function | Change from Phase 1 | Status |
| --- | --- | --- | --- | --- |
| Core Processing | ATMEGA328P-PU | Logic/Polling | No change | Finalized |
| Orientation | MPU9250 IMU | 9-DOF Motion | Changed from BNO055 | Finalized |
| Mapping | LIDAR-Lite v3 | Distance | No change | Finalized |
| Actuation | FS90R Servo | 360° Rotation | No change | Finalized |
| Communication | NRF24L01 | Wireless Link | No change | Finalized |
| Env - Pressure | BME280 | Temp/Hum/Press | Changed from BME680 | Finalized |
| Env - Gas | MQ135 | Air Quality | New Addition | Finalized |
| Thermal | AMG8833 | Thermal Heatmap | No change | Finalized |

# 8. Timeline and Roadmap

| Timeline | Objectives | Status |
| --- | --- | --- |
| Oct - Nov 2025 | Planning & Design, Component Procurement | ✅ Mostly Complete |
| Dec 2025 | Development, Firmware Integration, Testing | 🔄 In Progress |
| Jan 2026 | Sensor Fusion, Full System Integration, Field Testing | 📋 Paused |
| Feb 2026 | Documentation, Final Optimization | 📋 Paused |

## Current Blockers

Academic Exams: Development paused (resume early feburary 2026)

Component Delivery: Awaiting MPU9250 module

# 9. Next Steps (Post-Exam Resumption)

Upon resumption of work in feburary 2026, the following tasks are prioritized:

1. Sensor Fusion Algorithm Development (Yash - Embedded)

2. Environmental Sensor Integration (Yash - Embedded)

3. Complete Firmware Integration (Yash - Embedded)

4. API Linking for Base Station (Sannidhi & Shubham - Frontend)

5. Wireless Protocol Testing (Full Team)

6. Mechanical Enclosure Finalization (Varad - Design)

# 10. Risk Assessment and Mitigation

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Component Delays | Delay timeline | Backup components; phased procurement |
| Sensor Fusion Complexity | Firmware time | Use libraries (TinyIMU2); prototype on base station |
| MQ135 Calibration | Data accuracy | 48h warm-up protocol documented |
| Academic Interruptions | Project delays | Phased milestones; documentation during exam period |

# 11. Conclusion

Phase 2 is progressing steadily with a well-distributed workload across the team. The shift to MPU9250 and BME280+MQ135 (led by Sneha's research) maintains capabilities while reducing costs by ~₹1500. The frontend team (Sannidhi & Shubham) has completed the base station layout, and the embedded team (Yash) is advancing with sensor drivers. The design team (Varad) has validated mechanical viability through simulation.

The project remains financially on track and within budget constraints. Upon resumption after exams, the team expects to accelerate towards a fully functional prototype by end of January 2026.

Budget Efficiency Status: ✅ Revised spend maintains 50%+ safety margin under ₹10,000 budget cap.

Overall Project Health: ✅ Green - On schedule with manageable firmware complexity trade-offs.